MOODBUDS E-Commerce Website Phase-wise Development & Payment Plan

| Client MoodBuds Apparel | Category D2C Apparel Brand | Launch Men's Wear — Phase 1 | Version 2.0 — 2026 |
| --- | --- | --- | --- |

Total Project Value: ₹XXXXXX ¦ 5 Phases ¦ 20% Each ¦ ~50 Working Days

ABOUT THIS DOCUMENT

This document is your complete project blueprint for the MoodBuds website — written in plain language so you know exactly what you are getting, when you are getting it, and what you pay at each stage. The project is split into 5 clear phases. Each phase has a specific goal, a defined list of what will be delivered, and a payment tied to your approval of that phase.

Project at a Glance

| Item | Details |
| --- | --- |
| Website Name | MoodBuds E-Commerce Website |
| Brand | MoodBuds Apparel |
| First Launch Scope | Men's Wear — expandable to Kids & Women later |
| Total Investment | ₹X,XX,XXX |
| Total Timeline | Approx. 50 Working Days |
| Number of Phases | 5 Phases |
| Payment Per Phase | 20% of Total (₹XX,XXX per phase) |
| Payment Trigger | Client approval at end of each phase |

Phase-wise Payment Summary

| Phase | Title | Payment % | Amount | Est. Days |
| --- | --- | --- | --- | --- |
| Phase 1 | Advance — Project Kickoff | 20% | ₹XX,000 | Upfront |
| Phase 2 | Design & Look-and-Feel | 20% | ₹XX,000 | 10–14 days |
| Phase 3 | Website Functionality & Features | 20% | ₹XX,000 | 12–15 days |
| Phase 4 | Connections & Quality Testing | 20% | ₹XX,000 | 10–13 days |
| Phase 5 | Launch & Online Payments | 20% | ₹XX,000 | 7–10 days |
| TOTAL PROJECT |  | 100% | ₹X,XX,000 | ~50 Days |

PHASE 1 — ADVANCE: PROJECT KICKOFF

Payment: 20% ¦ ₹XX,000 ¦ Paid Before Work Begins

This is the advance payment that formally starts the project. Work begins only after this payment is received.

What Happens in This Phase

Once the advance is received, the team gets to work on the foundation of the entire project. This phase is about planning and preparing everything so that the actual design and development work runs smoothly.

What Gets Done

- Detailed discussion with you to finalise every page, feature, and flow of the website

- Finalisation of the complete list of website pages and screens

- Preparation of the website sitemap — a visual map of how every page connects to each other

- Agreement on the 9 mood categories (Happy, Confident, Cool, Professional, Party, Energetic, Romantic, Calm, Minimal) and how they will appear on the website

- Mood Quiz structure finalised — all 10 questions, 4 options each, and the logic for how each answer leads to a mood recommendation

What You Need to Provide

- Brand logo (high resolution)

- Product photos or confirmation of when they will be ready

- Reference websites you like (snitch, rarerabbit)

- Confirmation of mood categories and taglines

Payment Terms for Phase 1

Phase 1 payment of ₹XX,000 is collected before any work begins. This is standard practice for any professional web development engagement and confirms your commitment to the project. Once received: Kickoff call is scheduled → Scope document is finalised → Phase 2 work begins immediately.

PHASE 2 — DESIGN & LOOK-AND-FEEL

Payment: 20% ¦ ₹XX,000 ¦ Due on Your Design Approval

Payment is collected after you have reviewed and approved all the designs. No development begins until you are fully happy with how the website looks.

What This Phase Is About

This phase is purely about how your website will look and feel. Every page, every screen will be designed and shown to you for approval before any building begins. Think of this as the complete visual blueprint of your website.

Pages Designed in This Phase

Every page your customer will ever see will be designed:

- Home Page — with all sections: Mood Selection panel, Featured Collection, New Arrivals, Best Sellers and Footer

- Shop by Mood — each of the 9 moods gets its own banner, colour theme, and product view

- Shop by Category — browse by product type (shirts, hoodies, etc.)

- Product Page — full layout with photo gallery, price & savings display, size selector, Add to Cart, Wishlist, and customer reviews

- Mood Quiz — fully designed interactive quiz with 10 questions, animated transitions, progress bar, and final result screen showing 'Your Mood Today is: CONFIDENT' with matching product recommendations

- My Account — Login, Register, Forgot Password, and Dashboard (Order History, Saved Addresses, Wishlist, Profile)

- Cart Page — items, quantities, coupon code box, estimated delivery cost, and checkout button

- Checkout Page — address entry, delivery options, payment method selection, and order summary

- Order Confirmation & Order Tracking pages

- About Us and Contact Us pages (optional)

- Privacy Policy, Terms & Conditions, and Return & Refund Policy pages (not yet decided)

Design Style

- The look will be youthful, bold, and mood-driven — nothing like a generic clothing website

- Each of the 9 moods will have its own colour palette, banner artwork, and visual feel

- Mobile is designed first — your customers shop on phones, so every screen is mobile-perfect

Back-Office Design

The admin panel — your control room for managing the website — will also be fully designed:

- Add and edit products with all details: name, category, mood tags, sizes, pricing, photos, and discount

- View and update orders

- Create and manage discount coupon codes

Deliverables — What You Will Receive

Before Phase 2 payment is collected, you will have: ✔ Complete visual designs for every page ✔ Mood Quiz design — all 10 screens with transitions ✔ Admin panel screen designs

PHASE 3 — WEBSITE FUNCTIONALITY & FEATURES

Payment: 20% ¦ ₹XX,000 ¦ Due on Approval of Working Website on Staging

Payment collected after you try every feature, and confirm it all works as expected.

What This Phase Is About

This is where the website comes to life. The approved designs from Phase 2 are built into a fully working website. Every feature, every button, and every flow is made functional. At the end of this phase, you will have a complete working website on a test environment— only you can see it at this stage.

The Shopping Experience

- Customers can browse all products, filter by mood or category, and view full product details

- The Mood Quiz works end-to-end — customer answers 10 questions, gets a mood result, and is shown matching products

- Product pages show photo gallery, pricing with discount percentage, size availability

- Customers can add to wishlist

- Add to Cart works with live stock checking

Mood System

- All 9 moods are fully active — clicking a mood shows only products tagged to that mood, with the mood's unique banner and colour theme

- Products can be tagged to multiple moods (e.g., a black jacket can be Confident and Professional)

Mood Quiz — Fully Working

- Customer takes the quiz — answers about colour preferences, occasions, and personality

- The quiz intelligently tracks answers across 4 personality paths

- Final result screen shows the customer's mood for the day with a personalised message and 6–12 handpicked product suggestions

Customer Accounts

- Register with email or mobile number (with OTP verification)

- Login, forgot password, and OTP-based password reset — all working

- Customer dashboard: view past orders, track current orders, manage saved addresses, manage wishlist, and update profile

Cart & Checkout

- Cart saves items even if the customer closes the browser and comes back

- Coupon codes — customers can apply valid discount codes and see the deducted amount

- Checkout collects delivery address and lets customer choose their payment method (payment integration done in Phase 5)

Your Admin Control Panel — Fully Functional

- Add, edit, or remove products — with all details, photos, sizes, pricing, mood tags, and stock

- Manage mood categories

- View and update all orders — change status from 'Packed' to 'Shipped' to 'Delivered'

- Create discount coupon codes with expiry dates and usage limits

- View customer list

Future Growth Built In

The website is built to grow with your brand:

- Kids and Women categories can be added later without rebuilding anything

Deliverables — What You Will Receive

Before Phase 3 payment is collected, you will have access to: ✔ Complete working website ✔ All pages, features, and flows functional and testable ✔ Mood Quiz working with correct results ✔ Admin panel — you can add products, manage orders, create coupons

PHASE 4 — CONNECTIONS & QUALITY TESTING

Payment: 20% ¦ ₹XX,000 ¦ Due on Testing Sign-Off

Payment collected after all external services are connected and the full website passes a thorough quality check — signed off by you.

What This Phase Is About

We put the entire website through rigorous testing to make sure everything works perfectly before it goes live to the public.

Delivery Partner Connection (not yet finalized)

- Your website is connected to your chosen delivery partner (Shiprocket or Delhivery)

- When a customer places an order, it is automatically pushed to the delivery partner — no manual work needed

- A tracking number is automatically generated and assigned to the order

- The customer's tracking page shows live delivery status

Quality Testing — What We Check

Before we move to launch, we run a thorough check of every part of the website:

Complete Journey Testing

- Every customer path tested: Browse → Choose Mood → View Product → Add to Cart → Checkout → Confirmation

- Mood Quiz tested for all 9 possible results — each giving correct product recommendations

- All account features tested: register, login, OTP, forgot password, order history, address management, wishlist

- Coupon codes tested — valid codes, expired codes, already-used codes, wrong codes

- COD order and prepaid order flows both tested

- Admin panel tested — add product, edit product, update order status, create coupon, download report

Client Acceptance Testing

- You are given a full testing checklist to go through the website yourself

- 2 rounds of feedback and fixes included

- Any issues found will be fixed.

- All critical issues resolved before Phase 5 begins

Deliverables — What You Will Receive

Before Phase 4 payment is collected, you will have: ✔ Your sign-off on the full testing checklist

PHASE 5 — LAUNCH & ONLINE PAYMENTS

Payment: 20% ¦ ₹XX,000 ¦ Due on Website Going Live

Final payment collected the moment your website is publicly live and online payments are processing successfully.

What This Phase Is About

This is the big moment — your website goes live for the world to see and shop. In this phase, we set up your live online payment system, move the website to your permanent domain, and ensure everything is running perfectly. We also stay with you for 10 days after launch to handle any issues immediately.

Online Payment Setup

Your customers will be able to pay through multiple methods — all managed by a trusted Indian payment provider (Razorpay or Cashfree):

- Cash on Delivery

- When payment is successful — order is confirmed instantly

- If payment fails — customer sees a clear message and can retry without losing their cart

- Refunds for returns/cancellations are processed through the same payment system

Going Live

- Website is moved from staging (test) to your live domain

- SSL certificate confirmed — your website shows the secure padlock in the browser

- All product data, images, and settings carried over perfectly

- Admin panel accessible on live website — you can start adding real products

- A test purchase is made in live mode to confirm real payments work end-to-end

Pre-Launch Final Checklist

Everything below must pass before the website goes live: ✔ Live payment — test transaction successfully completed ✔ Full order flow — payment to confirmation to admin to delivery partner ✔ Secure connection verified on live domain ✔ Admin panel working on live website ✔ All login credentials and access handed over to you

After Launch — 10-Day Support

10 Days of Post-Launch Support — included in Phase 5, no extra charge: • Any urgent issues after launch are fixed as the top priority • Payment issues resolved immediately • One training session for you and your team on how to use the admin panel • Guidance on how to add your first products and process your first real orders Important: After the 10-day support window, new features or changes are a separate engagement.

What You Will Receive at Project Completion

Final Handover: ✔ Fully live MoodBuds website — publicly accessible to all customers ✔ Live online payments processing in all modes ✔ Complete admin panel access to manage your store independently ✔ All login credentials — website admin, hosting, payment dashboard ✔ Admin panel training completed ✔ Full ownership of the website transferred to you

PAYMENT TERMS & CONDITIONS

Core Principle: You only pay for a phase after you are satisfied with what was delivered in that phase. Each payment is tied to your approval — not to a date on a calendar. This ensures you are always in control of your investment.

| Phase | What Triggers Payment | Share | Amount | Due Within |
| --- | --- | --- | --- | --- |
| Phase 1 | Agreement signed — project officially begins | 20% | ₹XX,000 | Before work starts |
| Phase 2 | You approve all page designs | 20% | ₹XX,000 | Within 24 hrs of approval |
| Phase 3 | You confirm the staging website works as expected | 20% | ₹XX,000 | Within 24 hrs of approval |
| Phase 4 | You sign off on testing — all issues resolved | 20% | ₹XX,000 | Within 24 hrs of sign-off |
| Phase 5 | Website is live and payments are processing | 20% | ₹XX,000 | Within 24 hrs of go-live |

Additional Terms

- Revisions: 2 rounds of revisions included in each phase.

- Scope Changes: Any feature or page not listed in this document is considered additional scope and will be quoted separately before work begins. This protects both parties.

- Ownership: Full ownership of the website, code, and all content is transferred to you upon receipt of the final Phase 5 payment.

- Post-Launch Work: Any new features, pages, or changes requested after the 10-day support window are separate and will be quoted accordingly.

- Annual Maintenance: Ongoing website maintenance and support is available as a yearly contract — to be discussed separately after launch.